# Customer success plan

A 20-person agency · October–November 2026

Completed example — fictional customer and figures.

| Customer contact | Our contact | Last reviewed | Next review |
| --- | --- | --- | --- |
| Finance lead | Onboarding lead | 15 October 2026 | 29 October 2026, 10:00 UTC |

# Customer outcome

Cut the time spent preparing invoices each week and send invoices while the work is still fresh. The finance team currently rebuilds each invoice from project notes and spreadsheets.

# Success measures

| Measure | Starting point | Latest result | Target | By |
| --- | --- | --- | --- | --- |
| Weekly invoice preparation | 6 hours | 4.5 hours | 2 hours | 30 Nov |
| Work invoiced within 7 days | 65% | 78% | 95% | 30 Nov |

Source: the finance lead’s weekly time log and invoice records. Baseline: four weeks ending 25 September. Latest: week ending 9 October, with similar invoice volume.

# Actions and milestones

| Action / milestone | Owner | Due | Progress |
| --- | --- | --- | --- |
| Import the records and check the totals | Onboarding lead | 7 Oct | Done |
| Prepare the first invoice batch together | Finance lead | 9 Oct | Done |
| Add billing codes to the two unbilled jobs | Finance lead | 19 Oct | In progress |
| Run the next invoice batch without support | Finance lead | 23 Oct | Not started |

# Current blocker

Two completed jobs have no billing code, so they cannot be invoiced. The finance lead will confirm the codes with the project owners by 19 October.

# Review notes

15 October: preparation time fell to 4.5 hours. We agreed to fix the missing billing codes and run the next batch without support. Compare the new time log and invoicing rate on 29 October.

# Check-in schedule

Both leads will meet every other Thursday for 20 minutes. The finance lead will email the latest figures beforehand; urgent blockers go in the same email thread as they arise.